## Slide 1: W.L.Gore Status Report
CDMA Project

## Slide 2
Key Accomplishments Since Last Report | Key Upcoming Goals | Key Risks / Issues
Key items: Completed all planned Discovery sessions Completed initial draft of CI Design Document | In progress: Review of Design documentation for CI Design documentation for Marketing Environment Setup and Access allocation Finalizing scope for MVP Up Next: Review and Signoff of Design documents for CI and Marketing Complete Environment Setup Update JIRA with user stories Start Build | Risks: Delay in setting up with the environments will the delay the build phase and impact the schedule. Need environments to be ready by 10/30. Delay in finalizing the scope of MVP might delay the build phase and impact the schedule . Scope of MVP needs to be finalized by 10/26 Delay in providing the signoff for Design documents might delay in initiating the build and impact the schedule. Design needs to be signed off by 10/30 Issues: None
Executive Summary
In Discovery Phase: Completed all discovery sessions. Working in Design Documents and Environment setup
Current Status | Green
Schedule | Green
Scope | Green
Budget | Green
Attendees: Praveen, Jonathan, Amanda, Ray, Shradha, Ben, Jeff, Cindy, Sascha, Anthony

## Slide 3
Risks
Date | Type | Item Description | Due Date | Owner | Priority (H,M,L) | Mitigation | Status
10/10/2023 | Risk | Delay in setting up with the environments will the delay the build phase and impact the schedule | 10/23/2023 | W.L.GORE | H | Identfied all the licenses needed in setting up the environment in advance and working in provisioning access and roles to the team | In-Progress
10/5/2023 | Risk | Delay in identifying all the resources for the project will delay in initiating the project | 10/6/2023 | TTEC | H | Identified all the roles needed for the project and blocked them in advance. | Mitigated
10/13/2023 | Risk | Delay in finalizing the scope of MVP might delay the build phase and impact the schedule | 10/23/2023 | W.L.GORE | H | Scheduled sessions during the week of 10/16 to finalize the scope of MVP | In-Progress
10/12/2023 | Risk | Delay in providing the signoff for Design documents might delay in initiating the build and impact the schedule | 10/25/2023 | W.L.GORE | H | Planning to scheduled design review session in advance so that we can get a sign off at the earliest | Open

## Slide 4
Date | Type | Item Description | Due Date | Owner | Priority (H,M,L) | Notes | Status
10/16/2023 | Decision | Implement basic lead scoring for MVP. It would be used to train the trainers | NA | TTEC | M | Will schedule trainings before UAT | Closed
10/10/2023 | Decision | There is no suppression list to be implemented | NA | TTEC | M | It was discussed in Discovery session on 10/10 that there is no suppression list to implement | Closed
Issues / Decision Log

## Slide 5
Task List
Owner | Item Description | Start Date | Due Date | Notes | Status
Praveen Budamagunta | Schedule review design review meetings | 10/11/2023 | 10/12/2023 | Schedule Technical and Functional Design review sessions with the same audience in the Discovery session. Scheduled First session for CI Design review for Monday 10/23 | WIP
Praveen Budamagunta | Schedule additional sessions for Marketing Emails and Templates | 10/13/2023 | 10/13/2023 | Scheduled the session for 10/18 | Closed
Ray Fratto | Share User access details to WL Gore to setup and environment | 10/16/2023 | 10/17/2023 | Shared the details for Marketing . Will share the Detials for CI. | Closed
Praveen Budamagunta | Schedule additional discovery session for CI | 10/13/2023 | 10/16/2023 | Scheduled the session for 10/17 | Closed
Praveen Budamagunta | Update JIRA with all the tasks details | 10/23/2023 | 10/26/2023 | With detailed project plan finalized starting to update JIRA with tasks | Open

## Slide 6
Change log
Date | Item Description | Due Date | Owner | Notes | Status
 | None – Will finalize everything after discovery session |  |  |  | 

## Slide 7
Project Milestones | Target Start Date | Target Completion Date | Status | Notes
Initiate and Define | 10/02 | 10/31 | In Progress | Discovery sessions completed. Working on design documentation and Environment setup
Build | 11/1 | 1/19 | Not Started | 
Test and Train | 1/2 | 01/15 | Not Started | 
Deploy | 01/12 | 01/24 | Not Started | 
Transition and Accept | 1/22 | 2/12 | Not Started | 
Project Timeline and Milestones

## Slide 8
Task Name | Work | Duration | Start | Finish | % Complete | Predecessors | Resource Names
W.L.Gore Marketing and Customer Insights Migration | 3,580.46 hrs | 95.15 days | Thu 9/28/23 | Mon 2/12/24 | 5% |  | Client
Project Oversight | 594.5 hrs | 63.81 days | Thu 9/28/23 | Wed 12/27/23 | 11% |  | 
Initiate & Design | 358 hrs | 22 days | Mon 10/2/23 | Tue 10/31/23 | 52% |  | 
Initiate | 72 hrs | 4 days | Mon 10/2/23 | Thu 10/5/23 | 100% |  | 
Discovery & Design | 286 hrs | 18 days | Fri 10/6/23 | Tue 10/31/23 | 35% |  | 
Marketing | 96 hrs | 18 days | Fri 10/6/23 | Tue 10/31/23 | 25% | 17 | 
Discovery Session 0 - Current Process Review, Marketing App Demo | 6 hrs | 2 hrs | Fri 10/6/23 | Fri 10/6/23 | 100% |  | Ben Froese,Sharddha Jaitly,Stuti Mehta
Discovery Session 1 - Segmentation | 4 hrs | 2 hrs | Tue 10/10/23 | Tue 10/10/23 | 100% |  | Ben Froese,Sharddha Jaitly
Discovery Session 2 - Customer Journey Requirements | 4 hrs | 2 hrs | Wed 10/11/23 | Wed 10/11/23 | 100% |  | Ben Froese,Sharddha Jaitly
Discovery Session 3 - Maketing email Templates | 4 hrs | 2 hrs | Thu 10/12/23 | Thu 10/12/23 | 100% |  | Ben Froese,Sharddha Jaitly
Discovery Session 4 - Subscription Management | 4 hrs | 2 hrs | Fri 10/13/23 | Fri 10/13/23 | 100% |  | Ben Froese,Sharddha Jaitly
Discovery Session 5 - Landing Page / Marketing Pages , Lead Scoring / Lead Pipeline | 4 hrs | 2 hrs | Mon 10/16/23 | Mon 10/16/23 | 100% |  | Ben Froese,Sharddha Jaitly
Discovery Session 6 - Ping , Security Roles | 4 hrs | 2 hrs | Tue 10/17/23 | Tue 10/17/23 | 100% |  | Ben Froese,Sharddha Jaitly
Discovery Session 7 - Marketing Emails and Templates | 4 hrs | 2 hrs | Wed 10/18/23 | Wed 10/18/23 | 100% |  | Ben Froese,Sharddha Jaitly
Technical Requirements Documentation | 35 hrs | 46.67 hrs | Wed 10/18/23 | Wed 10/25/23 | 15% |  | Sharddha Jaitly[75%]
Technical Requirement Document - Internal Review | 6 hrs | 8 hrs | Wed 10/25/23 | Thu 10/26/23 | 0% | 29 | Sharddha Jaitly[75%]
Functional and Technical Design Document - Customer Review | 5 hrs | 6.67 hrs | Fri 10/27/23 | Fri 10/27/23 | 0% | 30 | Sharddha Jaitly[75%]
Functional and Technical Design Document - Customer Signoff | 16 hrs | 16 hrs | Mon 10/30/23 | Tue 10/31/23 | 0% | 31 | Client
Customer Insights | 190 hrs | 15 days | Fri 10/6/23 | Thu 10/26/23 | 44% |  | 
Discovery Session 1 - Introduction | 4 hrs | 2 hrs | Fri 10/6/23 | Fri 10/6/23 | 100% |  | Nina Zhang,Ray Fratto
Discovery Session 2 - Salesforce | 4 hrs | 2 hrs | Mon 10/9/23 | Mon 10/9/23 | 100% |  | Nina Zhang,Ray Fratto
Discovery Session 3 - Ping | 4 hrs | 2 hrs | Mon 10/9/23 | Mon 10/9/23 | 100% |  | Nina Zhang,Ray Fratto
Discovery Session 4 - Oracle | 4 hrs | 2 hrs | Tue 10/10/23 | Tue 10/10/23 | 100% |  | Nina Zhang,Ray Fratto
Discovery Session 5 - Strategic Marketing dataset | 4 hrs | 2 hrs | Wed 10/11/23 | Wed 10/11/23 | 100% |  | Kuldip Maharjan,Nina Zhang
Discovery Session 6 - Dynamics Contact and Marketing Activity | 4 hrs | 2 hrs | Wed 10/11/23 | Wed 10/11/23 | 100% |  | Kuldip Maharjan,Nina Zhang
Discovery Session 7 - Unification | 4 hrs | 2 hrs | Thu 10/12/23 | Thu 10/12/23 | 100% |  | Kuldip Maharjan,Nina Zhang
Discovery Session 8 - Export , Sales Force, KNIME/Dbeaver | 4 hrs | 2 hrs | Thu 10/12/23 | Thu 10/12/23 | 100% |  | Nina Zhang,Ray Fratto
Discovery Session 9 | 2 hrs | 2 hrs | Tue 10/17/23 | Tue 10/17/23 | 100% |  | Ray Fratto[30%]
Design Documentation | 40 hrs | 40 hrs | Fri 10/13/23 | Thu 10/19/23 | 75% | 41 | Nina Zhang
Design Document Internal Review | 4 hrs | 8 hrs | Thu 10/19/23 | Thu 10/19/23 | 0% |  | Nina Zhang[50%]
Design Document Customer Review | 92 hrs | 24 hrs | Fri 10/20/23 | Tue 10/24/23 | 0% | 44 | Kuldip Maharjan,Nina Zhang,Praveen Budamagunta,Ray Fratto
Design Document Customer Signoff | 8 hrs | 8 hrs | Wed 10/25/23 | Wed 10/25/23 | 0% | 45 | Praveen Budamagunta
Transition to GDC | 8 hrs | 8 hrs | Thu 10/26/23 | Thu 10/26/23 | 0% |  | Pavan Kumar
Transition to GDC | 4 hrs | 4 hrs | Thu 10/26/23 | Thu 10/26/23 | 0% |  | Nina Zhang

## Slide 9
Project Budget Hours as of Weekending Date: 10/20/2023
Dollars
Hours
Project Phase / Category | Budget Hours | Actual Hours (ATD) | Budget Remaining Hours | Estimate To Complete (ETC) | Estimate At Completion (EAC) | % of Budget | % of Completion
Initiate & Define | 315.5 | 229 | 86.5 | 86.5 | 315.5 | 72.58% | 72.58%
Build | 1,576.75 | 0 | 1576.75 | 1,576.75 | 1,576.75 | 0.00% | 0.00%
Test & Train | 137.5 | 0 | 137.5 | 137.5 | 137.5 | 0.00% | 0.00%
Deploy | 124.25 | 0 | 124.25 | 124.25 | 124.25 | 0.00% | 0.00%
Transition & Accept | 176 | 0 | 176 | 176 | 176 | 0.00% | 0.00%
Project Management | 492.25 | 98.5 | 393.75 | 393.75 | 492.25 | 20.01% | 20.01%
TOTAL | 2,822.25 | 327.50 | 2,494.75 | 2,494.75 | 2,822.25 | 11.60% | 11.60%
Project Phase / Category | Budget ($) | Actual ($) | Budget Remaining ($) | Estimate To Complete (ETC) | Estimate At Completion (EAC) | % of Budget | % of Completion
Initiate & Define | $64,565.00 | $51,710 | $12,855.00 | $12,855.00 | $64,565.00 | 80.09% | 80.09%
Build | $217,692.50 | $0 | $217,692.50 | $217,692.50 | $217,692.50 | 0.00% | 0.00%
Test & Train | $21,705.00 | $0 | $21,705.00 | $21,705.00 | $21,705.00 | 0.00% | 0.00%
Deploy | $23,217.50 | $0 | $23,217.50 | $23,217.50 | $23,217.50 | 0.00% | 0.00%
Transition & Accept | $26,400.00 | $0 | $26,400.00 | $26,400.00 | $26,400.00 | 0.00% | 0.00%
Project Management | $113,217.50 | $22,655.00 | $90,562.50 | $90,562.50 | $113,217.50 | 20.01% | 20.01%
TOTAL | $466,797.50 | $74,365.00 | $392,432.50 | $392,432.50 | $466,797.50 | 15.93% | 15.93%

## Slide 10
Project Billing / Payment
Time Period | Invoice # | Invoice Date | Amount Billed | Due Date | Amount Paid | Outstanding Balance
Has not shared any invoice yet